## Daily
Daily V9 | [11 empty] | TOT |  | K=kayam end |  |  |  | s=siam end |  |  | M=20m middle |  |  |  | m=15m middle |  |  |  | sc = stage cover |  |  |  |  | t = hex |  | VEA/S1 = old Val ends |  |  |  | VA/S2 = new val ends
| Max/Martin |  |  | ROSS |  |  | JESSE |  |  | MARLEY |  |  |  | PLASTICS | [12 empty] | Poles | [5 empty] | Other | [6 empty] | Other Metal - for office use only
[14 empty] | K1 | K8 F |  | M21 | M27 F |  |  | T1 |  | V 1 | VA1 |  |  | P2 | P8 | P14 | P20 |  |  | ad1 | ad2 | ad3 |  | auger driver |  |  | Bale rings = 46
2026-05-02 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-02 | K2 | K9 F | m5 | M24 | M28 F |  |  | T2 |  | V 2 | VS1 |  |  | P3 | P9 | P15 | P21 |  |  | a1 | a2 | a3 | a4 | pair of augers |  |  | Sidepoles = 491 (apprrox)
2026-05-03 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-03 | K3 | K10 F | m6 | M25 | sc1 F |  | s3 N | T3 F |  | V 3 | VA2 |  |  | P4 | P10 | P16 | X1 |  |  | a5 | a6
2026-05-04 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-04 | K6 F | K11 F | m7 N | M26 F | sc2 F |  | s4 N |  |  | V 4 | VS2 |  |  | P5 | P11 | P17 | X2 |  |  | ct1 | ct2 | ct3 | ct4 | Crew Tent
2026-05-05 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-05 | K7 F |  | m8 N |  | sc3f |  |  |  |  | V 5 |  |  |  | P6 | P12 | P18 | X3 |  |  | ct5
2026-05-06 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-06 | [13 empty] | P7 | P13 | P19 | X4 |  |  | Vb1 | Vb2 |  |  | Val Stake Basher
2026-05-07 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-07 |  | F = Ferrari | [7 empty] | T3 No rain flaps | [9 empty] | sb1 | sb2 | sb3 | sb4 | Kay Stake Basher
2026-05-08 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | 2026-05-08 |  | N = manufactured for 2018 season | [17 empty] | rd1 | rd2 | rd3 |  | Rock Drill
2026-05-09 | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  |  | TENT WASHING |  | 0 | 2026-05-09 |  |  | K1 | K8 |  | M21 | M27 | s3 |  |  |  | V 1 | VA1 |  | P2 | P8 | P14 | P20 | ad1 | ad2 | ad3 | rd1 | rd2 | rd3
2026-05-10 | [11 empty] | 0 | 2026-05-10 |  |  | K2 | K9 | m5 | M24 | M28 | s4 |  |  |  | V 2 | VS1 |  | P3 | P9 | P15 | P21 | a1 | a2 | a3 | a4 | a5 | a6
2026-05-11 |  |  | ANYONE WORKING IN FRANCE MUST HAVE | [7 empty] | 10 | 10 | 2026-05-11 |  |  | K3 | K10 | m6 | M25 | SC1 | T1 |  |  |  | V 3 | VA2 |  | P4 | P10 | P16 | X1 | ct1 | ct2 | ct3 | ct4 | ct5
2026-05-12 |  |  | MEDICAL | [7 empty] | 10 | 10 | 2026-05-12 |  |  | K6 | K11 | m7 | M26 F | SC2 | T2 |  |  |  | V 4 | VS2 |  | P5 | P11 | P17 | X2 | Vb1 | Vb2
2026-05-13 |  |  | SIPISI + AI | [7 empty] | 10 | 10 | 2026-05-13 |  |  | K7 |  | m8 |  | SC3 | T3 |  |  |  | V 5 |  |  | P6 | P12 | P18 | X3 | sb1 | sb2 | sb3 | sb4
2026-05-14 |  |  | CONTRACT | [7 empty] | 10 | 10 | 2026-05-14 | [14 empty] | P7 | P13 | P19 | X4
2026-05-15 | [9 empty] | LD 1,2 OX AM | 10 | 10 | 2026-05-15 | [19 empty] | 1 | 2
2026-05-16 | [6 empty] | TRAINING MY @ CAT |  | UNLD 1,2 | BUILD | 10 | 10 | 2026-05-16 | [19 empty] | K8 | P4 | P5
2026-05-17 | [6 empty] | TRAINING MY @ CAT |  |  | BUILD | 10 | 10 | 2026-05-17 | [19 empty] | K9 | P3 | sb1
2026-05-18 | 6 START | 6 |  |  |  |  | TRAINING MY @ CAT |  |  | BUILD | 10 | 16 | 2026-05-18 | [19 empty] | M24 | P2 | ct1
2026-05-19 | LD 3,4,5 OX | 6 |  |  |  |  | TRAINING MY @ CAT |  |  | BUILD | 10 | 16 | 2026-05-19 |  | 3 | 4 | 5 | [15 empty] | M26 | M25
2026-05-20 | CM1 | 6 |  |  |  |  | TRAINING MY @ CAT |  |  | UP 20/5 @ 08:00 | 10 | 16 | 2026-05-20 | C1 | 3 | 4 | 5 | [15 empty] | CATALYST
2026-05-21 | BUILD | 11 | UNLD 3,4,5 |  |  |  | TRAINING MY @ CAT |  | CM2 5 < Red | CATALYST | 5 | 16 | 2026-05-21 |  | V1 | [17 empty] | K8 | P2
2026-05-22 | BUILD | 11 |  |  |  |  | TRAINING MY @ CAT |  |  | 8K KMMMK | 5 | 16 | 2026-05-22 |  | V2 | [17 empty] | M25 | P3
2026-05-23 | BUILD | 11 |  |  |  |  | TRAINING MY @ CAT |  |  | Camping | 5 | 16 | 2026-05-23 |  | VA1 | [17 empty] | M26 | P4
2026-05-24 | BUILD | 11 |  |  |  |  | TRAINING MY @ CAT |  |  | Self-cater build/break | 5 | 16 | 2026-05-24 |  | VS1 | [17 empty] | M24 | P5
2026-05-25 | BUILD | 11 |  |  |  |  | TRAINING MY @ CAT |  |  | Catering on show days | 5 | 16 | 2026-05-25 |  | ad1 | [17 empty] | K9
2026-05-26 | BUILD | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  | 3 START | Royal Nrlfk Showgrnd | 8 | 19 | 2026-05-26 |  | Vb1
2026-05-27 | BUILD | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  |  | DN 27/5 @ 08:00 | 8 | 19 | 2026-05-27 |  | ct2
2026-05-28 | BUILD | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  |  | BREAK | 8 | 19 | 2026-05-28 | [19 empty] | sb1
2026-05-29 | UP 29/5 @ 20:00 | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  |  | BREAK | 8 | 19 | 2026-05-29 |  | WLG | [17 empty] | ct1
2026-05-30 | WLG | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  | UNLD 8,9 OX | LD 8,9 | 8 | 19 | 2026-05-30 | [17 empty] | 8 | 9
2026-05-31 | 6 POLE VAL | 11 | OHS COURSE |  |  |  | TRAINING MY @ CAT |  |  |  | 8 | 19 | 2026-05-31 |  | V1 | [15 empty] | K8 | K9 | M24 | M26
2026-06-01 | Bois de Vincennes | 11 | OHS COURSE | [7 empty] | 8 | 19 | 2026-06-01 |  | V2 | [8 empty] | K1 | K10 | M28 | SC1 | T1 | V 3 | VA2 | M25 | P2 | P3 | P4
2026-06-02 | Paris, FR | 11 | OHS COURSE |  |  |  |  | 8 |  | 8 < ORNG | 0 | 19 | 2026-06-02 |  | VA1 | [8 empty] | K2 | K11 | m5 | SC2 | T3 | V 4 | VS2 | P5 | sb1 | ct1
2026-06-03 | Semi-Catered | 11 | OHS COURSE |  |  |  |  | 8 |  |  |  | 19 | 2026-06-03 |  | VS1 | [8 empty] | K3 | M25 | m6 | SC3 | T2 | V 5
2026-06-04 | Camping off site | 11 | OHS COURSE |  |  |  |  | 8 |  |  |  | 19 | 2026-06-04 | [10 empty] | K8 | M26 F | m7 | s3 | ad2 | ad3 | rd1
2026-06-05 |  | 11 | OHS COURSE |  |  |  |  | 8 |  |  |  | 19 | 2026-06-05 | [10 empty] | K9 | M27 | m8 | s4 | a1 | ct1 | rd2
2026-06-06 |  | 11 | OHS COURSE |  |  |  |  | 8 |  |  |  | 19 | 2026-06-06 | [10 empty] | K6 | M21 | P17 | X1 | a2 | ct4 | rd3
2026-06-07 |  | 11 | OHS COURSE |  |  |  | LD 10,11 OX | 8 |  |  |  | 19 | 2026-06-07 | [10 empty] | K7 | M24 | P18 | X2 | a3 | ct5 | ct3 |  | C2 | 10 | 11
2026-06-08 |  | 11 | OHS COURSE |  |  |  | CM 5 & 6 | 8 |  |  |  | 19 | 2026-06-08 | [10 empty] | P2 | P11 | P19 | X3 | a4 | Vb2 |  |  |  | 10 | 11
2026-06-09 |  | 11 | OHS COURSE |  |  | UNLD 10,11 | BUILD | 8 |  |  |  | 19 | 2026-06-09 | [10 empty] | P3 | P12 | P20 | X4 | a5 | sb3 | sb1 |  |  | K10 | P13 | a2
2026-06-10 | DN 10/6 @ 08:00 | 16 | LOCAL X 3 TBC |  |  | 5 < Red | BUILD | 3 |  |  |  | 19 | 2026-06-10 | [10 empty] | P4 | P13 | P21 |  | a6 | sb4 |  |  |  | M26 F | P14 | ad3
2026-06-11 | BREAK | 16 | LOCAL X 3 TBC |  |  |  | BUILD 3PM FINISH | 3 |  |  |  | 19 | 2026-06-11 |  | ad1 | [8 empty] | P5 | P14 |  |  |  | sb2 |  |  |  | m5 | P15 | ct4
2026-06-12 | BREAK | 16 | LOCAL X 3 TBC |  |  |  | BUILD | 3 |  |  |  | 19 | 2026-06-12 |  | ct2 | [8 empty] | P6 | P15 | [7 empty] | m6 | P16 | sb3
2026-06-13 | BREAK | 11 | LD 12,13,14 | 5 > ORNG |  |  | BUILD | 8 |  |  |  | 19 | 2026-06-13 |  | Vb1 | [8 empty] | P7 | P16 | [7 empty] | SC3 | P10
2026-06-14 | CM4 | 9 |  | CM3 2 > GRN RM | 2 |  | BUILD | 8 |  |  |  | 19 | 2026-06-14 |  | 12 | 13 | 14 | [6 empty] | P8 | [8 empty] | s3
2026-06-15 |  | 9 |  |  | 2 |  | BUILD 3PM FINISH | 8 |  |  |  | 19 | 2026-06-15 |  | 12 | 13 | 14 | [6 empty] | P9 | [8 empty] | s4
2026-06-16 | BUILD | 9 |  | 5 START | 7 |  | BUILD | 8 |  |  |  | 24 | 2026-06-16 |  | V1 | [8 empty] | P10
2026-06-17 | BUILD | 11 | UNLD 12,13,14 |  | 7 |  | All UP 18:00 @ 17/6/26 | 6 | 2 < RED CM15 |  |  | 24 | 2026-06-17 |  | V2 | [17 empty] | SOLIDAYS
2026-06-18 | BUILD | 11 |  | LD 1516,17 OX | 7 |  | 3PM FINISH | 6 |  |  |  | 24 | 2026-06-18 |  | VA1 | [12 empty] | 15 | 16 | 17
2026-06-19 | BUILD | 11 | UNLD 15,16,17 | BUILD | 9 | 1 START | SOLIDAYS | 4 | CM7 2<GREEN |  |  | 24 | 2026-06-19 |  | VS1 | [12 empty] | K11 | P17 | T3 |  |  | K10 | P10 | s3
2026-06-20 | BUILD | 11 |  | BUILD | 9 |  | 4S sms + 6SC KMmSC | 4 |  |  |  | 24 | 2026-06-20 |  | ad1 | [12 empty] | M27 | P18 | ad2 |  |  | M26 | P13 | m5
2026-06-21 | BUILD | 11 |  | BUILD | 9 |  | Longchamp Racecourse | 4 |  |  |  | 24 | 2026-06-21 |  | Vb1 | [12 empty] | P11 | P19 | a1 |  |  | m6 | P14 | s4
2026-06-22 | BUILD | 11 |  | BUILD | 9 |  | Paris FR | 4 |  |  |  | 24 | 2026-06-22 |  | ct2 | [12 empty] | P12 | P20 | ct1 |  |  | SC3 | P15
2026-06-23 | 20:00 @ 23/6/26 | 11 |  | BUILD | 9 |  | Camping off site | 4 |  |  |  | 24 | 2026-06-23 |  | ROSKILDE | [9 empty] | VA2 |  |  | M28 | P21 | sb4 |  |  |  | P16
2026-06-24 | ROSKILDE | 11 |  | BUILD | 9 |  | Catering | 4 |  |  |  | 24 | 2026-06-24 | [11 empty] | VS2 |  |  | m7 | SC1
2026-06-25 | 6V | 11 |  | early Handover if pos | 8 | 1 FINISH |  | 4 |  |  |  | 23 | 2026-06-25 | [11 empty] | V 3 |  |  | m8 | SC2
2026-06-26 | Roskilde, DK | 11 |  | 08:00 @ 26/6/26 | 8 |  |  | 4 |  |  |  | 23 | 2026-06-26 |  | V1 |  |  |  |  | K1 |  | P6 |  |  | V 4 |  |  | SILVERSTONE
2026-06-27 | Camping on site | 11 |  | Silverstone F1 | 8 |  |  | 4 |  |  |  | 23 | 2026-06-27 |  | V2 |  |  |  |  | K2 | X1 | P7 | ct4 |  | V 5
2026-06-28 | Catering | 11 |  | 14Pole DBL SC | 4 | CM8 4> ORNG |  | 8 |  |  |  | 23 | 2026-06-28 |  | VA1 |  |  |  |  | K3 | X2 | P8 | ct3 | a2 |  |  |  |  | K11
2026-06-29 |  | 11 |  | SCmMtMmSCK | 4 |  |  | 8 |  |  |  | 23 | 2026-06-29 |  | VS1 |  |  |  |  | K8 | X3 | P2 | ct5 | a3 | sb3 |  |  | M28 | T3 | M27
2026-06-30 |  | 11 |  | Silverstone Track | 4 |  |  | 8 |  |  |  | 23 | 2026-06-30 | [6 empty] | K9 | X4 | P3 | rd1 | a4 | Vb2 |  |  | m8 |  | m7
2026-07-01 |  | 11 |  | Towcester, UK | 4 | VENUE OPEN 12:00 | 4S@13:00 6SC@18:00 | 8 |  |  |  | 23 | 2026-07-01 | [6 empty] | K6 |  | P4 | rd2 | a5 | sb2 | sb1 |  | SC1 |  | SC2
2026-07-02 |  | 11 |  | CORPORATE | 4 |  | BREAK 3PM FINISH | 8 |  |  |  | 23 | 2026-07-02 | [6 empty] | K7 | T2 | P5 | rd3 | a6 | ad3 | K10 | [6 empty] | a2
2026-07-03 |  | 11 |  | CLIENT | 4 |  | BREAK | 8 |  |  |  | 23 | 2026-07-03 | [6 empty] | K10 | T1 | P9 |  |  |  | M26 |  | P11 |  |  |  |  | ad3
2026-07-04 |  | 11 |  | Camping on site TBC | 4 |  | BREAK | 8 |  |  |  | 23 | 2026-07-04 | [6 empty] | M21 | m5 | P13 |  |  | P13 | m5 |  | P12 |  |  |  |  | ct4 | sb3
2026-07-05 |  | 11 |  | Catering 29th-5th only | 4 | Ld 20,21 | BREAK | 8 |  |  |  | 23 | 2026-07-05 | [6 empty] | M25 | m6 | P14 |  | a2 | P14 | m6 |  | P17 |  |  |  | C2
2026-07-06 | 13:00 @ 7/6/26 | 11 |  |  | 4 |  | CM 13 & 14 | 8 |  |  |  | 23 | 2026-07-06 | [6 empty] | M24 | SC3 | P15 |  | ad3 | P15 | SC3 |  | P18 |  |  |  |  | 20 | 21
2026-07-07 | BREAK | 11 |  | Stage Clear | 4 |  | unld 20,21 OX | 8 |  |  |  | 23 | 2026-07-07 |  | ad1 |  |  |  |  | M26 | s3 | P16 |  | ct4 | P16 | s3 | << | P19 |  |  | << | << | 20 | 21
2026-07-08 | BREAK | 11 |  |  | 4 |  |  | 8 |  |  |  | 23 | 2026-07-08 |  | ct2 | [5 empty] | s4 | P10 |  | sb3 | P10 | s4 |  | P20
2026-07-09 | BREAK | 11 |  |  | 7 |  | 2<GRN / 4>BLU | 2 | 1 START | LD 27,28 OX | 5 | 25 | 2026-07-09 |  | Vb1 | [7 empty] | 27 | 28 |  |  |  | P21
2026-07-10 | BREAK | 7 | CM9/10 3>BLU 1>GRN | 08:00 @ 10/7/26 | 10 | 3 START |  | 2 |  |  | 8 | 27 | 2026-07-10 | [9 empty] | 27 | 28 | [14 empty] | K11 | m7 | P11
2026-07-11 | BREAK/ LD 22,23,24 | 5 | CM11 & 18 2 > ORNG | BREAK | 10 |  | LD 29,30,31 OX | 4 | UNLD 27,28 | BUILD | 8 | 27 | 2026-07-11 | [8 empty] | >>> | K3 | sb3 | P15 | >>> | >>> | ad2 |  |  | >>> | 29 | 30 | 31 |  |  |  |  | M27 | m8 | P12
2026-07-12 |  | 5 | CM20 | BREAK | 10 |  | BUILD / UNLD 29,30,31 | 4 |  | BUILD | 8 | 27 | 2026-07-12 | C1 | 22 | 23 | 24 | [5 empty] | m5 | ct5 | P16 |  |  | a1 |  |  |  | K8 | P6 | sb2 |  |  |  |  | M28 | SC1 | P17
2026-07-13 | LD 25, 26 OX | 5 | CM19 | BREAK | 10 |  | WF BUILD 2K | 4 |  | BUILD | 8 | 27 | 2026-07-13 |  | 22 | 23 | 24 |  |  | 25 | 26 |  | m6 | P9 | P10 |  |  | ct1 |  |  |  | K9 | P7 | sb1 |  |  |  |  | T3 | SC2 | P18
2026-07-14 | BUILD | 5 | UNLD 22-26 | BREAK/LD 32,33,34 | 8 | 2 FINISH | WF BUILD 2K | 4 |  | BUILD | 8 | 25 | 2026-07-14 |  | >> | >> | >> | V1 |  |  | V3 |  | s3 | P13 | P14 |  |  | sb4 |  |  | >> | K6 | P8 |  | >> | 32 | 33 | 34 | ad2 | ct1 | P19
2026-07-15 | BUILD | 9 |  | UNLD 32,33,34 OX | 7 | 1 < RED | WF BUILD 2K | 4 | CM12 3 < RED | 08:00 @ 15/7/26 | 5 | 25 | 2026-07-15 |  |  |  |  | V2 |  |  | V4 |  | MAGNITUDE | [8 empty] | K7 | P2 | [5 empty] | a1 | sb4 | P20
2026-07-16 | BUILD | 11 |  | BUILD | 7 | 2 < RED | WF BUILD | 2 |  | MAGNITUDE | 5 | 25 | 2026-07-16 |  |  |  |  | VA1 |  |  | a2 | [10 empty] | K10 | P3 |  |  | K1 | SC1 |  | ct4 | ad2 | P21
2026-07-17 | BUILD | 11 |  | BUILD | 7 |  | WF BUILD | 2 |  | 6 Pole Siam/Kayam | 5 | 25 | 2026-07-17 |  |  |  |  | VS1 |  |  |  |  | K3 | [8 empty] | M25 | P4 |  |  | K2 | SC2 |  | ct1 | ad3
2026-07-18 | BUILD | 11 |  | BUILD | 7 |  | WF BUILD | 2 |  | smmK | 5 | 25 | 2026-07-18 |  |  |  |  | ad1 |  |  |  |  | m5 | P15 | [7 empty] | M26 |  |  |  | K11 | SC3 | P5 | rd1 | sb4
2026-07-19 | BUILD | 11 |  | BUILD | 7 |  | WF BUILD | 2 |  | Lendrick Muir | 5 | 25 | 2026-07-19 |  |  |  |  | Vb1 |  |  |  |  | m6 | P16 | [7 empty] | T2 | ct3 |  |  | M21 | m7 | P11 | rd2 | Vb2
2026-07-20 | BUILD | 11 |  | 08:00 @ 20/7/26 | 7 |  |  | 2 |  | Scotland | 5 | 25 | 2026-07-20 |  |  |  |  | ct2 |  |  |  |  | s3 | P10 | [7 empty] | WILDFIRES |  |  |  | M24 | m8 | P12 | rd3
2026-07-21 | BUILD | 11 |  | WILDFIRES | 6 | 1 FINISH | LD 35,36 OX | 2 |  |  | 5 | 24 | 2026-07-21 | [14 empty] | 35 | <<< | 35 | <<< |  | K8 |  | <<< | M27 | s4 | P17 | a1
2026-07-22 | 08:00 @ 22/7/26 | 11 |  | 10CT KMtMKK | 6 |  | 3 START | 6 | 1 < ORANGE | Camping off site | 4 | 27 | 2026-07-22 |  |  |  |  | NEW DAY | [9 empty] | 35 |  |  |  | M25 | T2 | M26 |  | M28 |  | P18 | a3 | VA2
2026-07-23 | NEW DAY | 11 |  | + 2K KK | 4 | 2 > BLUE | BUILD | 6 | LD 36 | Self-catering | 6 | 27 | 2026-07-23 | [12 empty] | 36>> | K11 | ct1 | P13 |  |  | K9 |  | K10 |  | T1 |  | P19 | a4 | VS2
2026-07-24 | 10V | 11 |  | Wiston Sussex | 4 | UNLD 35,36 | BUILD | 6 |  | 08:00 @ 24/7/26 | 6 | 27 | 2026-07-24 |  |  |  |  | VA1 | [8 empty] | M28 | sb4 | P14 |  |  | P6 |  |  |  | T3 |  | P20 | a5 | V 5
2026-07-25 | Norfolk Showground | 11 |  | Self Catering | 4 |  | BUILD | 6 |  | BREAK | 6 | 27 | 2026-07-25 |  |  |  |  | V1 |  |  |  |  | P9 | P13 | P14 |  | m8 | s4 | P9 |  |  | P7 | P3 | K6 |  |  |  | P21 | a6
2026-07-26 | Norwich, UK | 11 |  | Camp on Site | 4 |  | BUILD | 6 |  | BREAK | 6 | 27 | 2026-07-26 |  |  |  |  | V2 |  |  |  |  | sb3 | [8 empty] | P8 | P4 | K7
2026-07-27 | Camping on site | 11 |  | 20:00 @ 27/7/26 | 4 | UNLD 37 | 08:00 @ 27/7/26 | 3 | 3 FINISH | BREAK / LD 37,38 | 6 | 24 | 2026-07-27 |  |  |  |  | V3 |  |  |  |  | ct5 |  |  | 37>> | FBTS |  |  | m5 |  | P2 |  |  |  |  | K3 | sb3 |  | K3 | sb3
2026-07-28 | Catering | 11 |  | BREAK | 7 |  | FBTS | 4 | 1 < ORNG | 3 < GREEN | 3 | 25 | 2026-07-28 |  |  |  |  | V4 |  |  |  |  | 38 | >> | >> | >> |  |  |  | m6 | >> | ct3 |  |  | >> | >> | P15 | ct5 |  | P15 | ct5
2026-07-29 |  | 11 |  | BREAK | 7 |  | 6 Pole Siam/Kayam | 4 |  | UNLD 38 OX | 2 | 24 | 2026-07-29 |  |  |  |  | VS1 | [8 empty] | K11 |  | P13 |  |  | sb2 |  |  |  |  | P16 |  |  | P16
2026-07-30 |  | 11 |  | BREAK | 9 |  | smMK | 4 |  | 2 < Green | 0 | 24 | 2026-07-30 | [13 empty] | M28 |  | P14 |  |  | sb1 |  |  |  |  | P10 |  |  | P10
2026-07-31 |  | 11 |  | BREAK | 9 |  | North Berwick | 4 |  |  |  | 24 | 2026-07-31 | [13 empty] | m8 |  | P9 | [7 empty] | s3 |  |  | s3
2026-08-01 |  | 11 | LD 39,40,41 | BREAK | 9 |  | Scotland | 4 |  |  |  | 24 | 2026-08-01 | [13 empty] | s4
2026-08-02 | 08:00 @ 2/8/26 | 11 |  | UNLD 39,40,41 OX | 9 |  | Camping off site | 4 |  |  |  | 24 | 2026-08-02 | [18 empty] | 39 | 40 | 41
2026-08-03 | BREAK TBC | 11 |  |  | 9 |  | Self Catering | 4 |  |  |  | 24 | 2026-08-03 |  |  |  |  | ad1 | a2 | [12 empty] | K8 | P6 | sb2 | K7 | P2 | M25 | P4 | T2 | ct3
2026-08-04 | BREAK TBC | 11 |  | 4 > ORNG | 5 |  |  | 8 |  |  |  | 24 | 2026-08-04 |  |  |  |  | Vb1 | [13 empty] | K9 | P7 | K6 | P8 | K10 | P3 | M26 |  | sb1
2026-08-05 | BREAK TBC | 11 |  |  | 5 |  |  | 8 |  |  |  | 24 | 2026-08-05 |  |  |  |  | ct2
2026-08-06 | BREAK TBC | 11 |  | 2 FINISH | 3 |  |  | 8 |  |  |  | 22 | 2026-08-06 | [26 empty] | T1
2026-08-07 | BREAK TBC | 11 | LD 44,45,46,47,48 |  | 3 |  |  | 8 |  |  |  | 22 | 2026-08-07 | [19 empty] | K1 | K8 |  | M21 | M27 |  |  | T2
2026-08-08 | UNLD 44,45,46,47,48 OX | 11 |  |  | 3 |  |  | 8 |  |  |  | 22 | 2026-08-08 |  |  |  |  | 44 | 45 | 46 | 47 | 48 | [10 empty] | K2 | K9 | m5 | M24 | M28 |  | s3 | T3
2026-08-09 |  | 11 |  |  | 3 |  |  | 8 |  |  |  | 22 | 2026-08-09 |  |  |  |  | 44 | 45 | 46 | 47 | 48 | [10 empty] | K3 | K10 | m6 | M25 | SC1 |  | s4 |  | rd2
2026-08-10 |  | 14 |  | 3 < RED | 4 |  |  | 8 |  |  |  | 26 | 2026-08-10 |  |  |  |  | 44 | 45 | 46 | 47 | 48 | [10 empty] | K6 | K11 | m7 | M26 F | SC2 |  |  |  | a5 | rd3
2026-08-11 | LD 49 OX | 14 |  |  | 0 |  |  | 8 |  |  |  | 22 | 2026-08-11 |  |  |  |  | 44 | 45 | 46 | 47 | 48 | 49 | << | << | << |  |  |  | << |  |  | K7 |  | m8 |  | SC3 |  |  |  | ct5 | a6
2026-08-12 | BUILD | 14 | UNLD 44-49 |  | 0 |  | 08:00 @ 12/8/26 | 8 |  |  |  | 22 | 2026-08-12 |  |  |  |  | 44: V 1; 45: VA1; 46: ad2 | [7 empty] | K11 | P13 | P2 | P8 | P14 | P20 |  |  | ad1 |  | ad3 | rd1
2026-08-13 | BUILD | 14 |  |  | 0 |  | BREAK | 8 |  |  |  | 22 | 2026-08-13 |  |  |  |  | 44: V 2; 45: VS1; 46: a2 |  |  |  | ct1 | m5 |  |  | M28 | P14 | P3 | P9 | P15 | P21 |  |  | a1 |  | a3 | a4
2026-08-14 | BUILD | 14 |  |  | 0 | LD 42,43 | BREAK | 8 |  |  |  | 22 | 2026-08-14 |  |  |  |  | 44: V 3; 45: Vb1; 46: ct2 |  |  |  | sb4 | m6 |  |  | m8 | P9 | P4 | P10 | P16 | X1 |  | VA2 | ct1 |  | ct3 | ct4
2026-08-15 | BUILD | 14 |  |  | 0 |  |  | 8 |  |  |  | 22 | 2026-08-15 |  |  |  |  | 44: V 4; 46: ct3 |  |  |  | 42 | 43 |  |  | s4 | m5 | P5 | P11 | P17 | X2 |  | VS2 |  | Vb2
2026-08-16 | BUILD | 14 |  |  | 0 |  | UNLD 42,43 OX | 8 |  |  |  | 22 | 2026-08-16 |  |  |  |  | 44: V 5 |  |  |  | 42 | 43 | >> | >> | ct1 | m6 | P6 | P12 | P18 | X3 | V 5 |  | sb1 | sb2 | sb3 | sb4
2026-08-17 | BUILD | 14 |  |  | 0 |  | 1 FINISH | 7 |  |  |  | 21 | 2026-08-17 | [17 empty] | sb4 |  | P7 | P13 | P19 | X4
2026-08-18 | BUILD | 14 | 3 > GREEN |  | 8 |  | 5 < GREEN / 2 < Red | 0 |  |  |  | 22 | 2026-08-18
2026-08-19 | BUILD | 14 |  | LD 54 OX | 8 | [6 empty] | 22 | 2026-08-19 | [12 empty] | 54 | 54 | << | 54 | << | 54
2026-08-20 | BUILD | 14 |  | BUILD | 8 | UNLD 54 | [5 empty] | 22 | 2026-08-20 | [12 empty] | K11 | P20 | ad1
2026-08-21 | 21/8/26 @ 08:00 | 14 |  | BUILD | 8 | [6 empty] | 22 | 2026-08-21 |  |  |  |  | 44: READING |  |  | M28 | P21 | a1
2026-08-22 |  | 14 |  | BUILD | 8 | [6 empty] | 22 | 2026-08-22 | [12 empty] | SC3 | sb1 | ct1 |  |  | K1 | M21 | m5 |  | P2 | P8 | P14 | X1
2026-08-23 | FESTIVAL REPUBLIC | 14 |  | 08:00 @ 23/8/26 | 8 | [6 empty] | 22 | 2026-08-23 | [12 empty] | SHAMBALA |  |  |  |  | K2 | M24 | m6 |  | P3 | P9 | P15 | X2
2026-08-24 | 12V | 14 |  | SHAMBALA | 8 | [6 empty] | 22 | 2026-08-24 |  |  |  |  | 44: VA1 | [7 empty] | K3 | M25 | m7 |  | P4 | P10 | P16 | X3
2026-08-25 | READING | 14 |  | 4SC KMSC | 8 | [6 empty] | 22 | 2026-08-25 |  |  |  |  | 44: V 1 | [7 empty] | K6 | M26 F | m8 |  | P5 | P11 | P17 | X4
2026-08-26 |  | 14 |  | Kelmarsh Hall | 8 | [6 empty] | 22 | 2026-08-26 |  |  |  |  | 44: V 2 |  |  | K11 | P20 |  |  |  | K7 | M27 | s3 |  | P6 | P12 | P18
2026-08-27 | ground concrete needs | 14 |  | Northamptonshire | 8 | [6 empty] | 22 | 2026-08-27 |  |  |  |  | 44: V 3 |  |  | M28 | P21 |  |  |  | K8 | SC1 | s4 |  | P7 | P13 | P19
2026-08-28 | reviewing | 14 |  |  | 8 | [6 empty] | 22 | 2026-08-28 |  |  |  |  | 44: V 4 |  |  | SC3 |  |  |  |  | K9 | SC2 | T1 |  |  | ct5 | ct4
2026-08-29 |  | 14 |  | Camping on site | 8 | [6 empty] | 22 | 2026-08-29 |  |  |  |  | 44: V 5 | [7 empty] | K10 |  | T2 |  | VA2 | Vb2
2026-08-30 | HSE WILL BE THERE | 14 |  | Catering build & | 8 | [6 empty] | 22 | 2026-08-30 |  |  |  |  | 44: VS1 | [9 empty] | T3 |  | VS2 | sb2 | sb3 | sb4
2026-08-31 |  | 14 |  | break only | 8 | [6 empty] | 22 | 2026-08-31 | [21 empty] | rd1 | rd2 | rd3
2026-09-01 |  | 14 | Who's Loading Dis X? | 08:00 @ 1/9/26 | 8 | [6 empty] | 22 | 2026-09-01 | [21 empty] | a3 | a5 | a6 | ad3 | a4
2026-09-02 | 2/9/26 @ 20:00 | 14 | LD 56,57 OX | BREAK / LOADOUT | 8 | LD 55 | [5 empty] | 22 | 2026-09-02 | [12 empty] | sb1 | ct1 | a1 | ad1 | [5 empty] | 56 | 57
2026-09-03 | BREAK | 14 | UNLD 55 OX | 1 START / 1 FINISH | 8 | CM16 | [5 empty] | 22 | 2026-09-03 |  |  |  |  | 44: Vb1; 45: a2 | [5 empty] | 55 | [5 empty] | 56 | 57
2026-09-04 | BREAK | 14 |  | BUILD | 8 | UNLD 56,57 | [5 empty] | 22 | 2026-09-04 |  |  |  |  | 44: ad2; 45: ct2 | V 1 | VA1 | ad2 | V 1 | VA1 | K11 | P20 | ad1 |  |  |  | K9 | M24 | P2 | P6
2026-09-05 | BREAK | 14 |  | BUILD | 8 | [6 empty] | 22 | 2026-09-05 |  |  |  |  | 45: ct3 | V 2 | VS1 | a2 | V 2 | VS1 | M28 | P21 | a1 |  |  |  | K10 | M25 | P3 | ct5
2026-09-06 | BREAK | 14 |  | BUILD | 8 | [6 empty] | 22 | 2026-09-06 | [10 empty] | V 3 | Vb1 | ct2 | V 3 | VA2 | SC3 | sb1 | ct1 |  |  |  |  | M26 F | P4 | sb2
2026-09-07 | BREAK | 14 |  | BUILD | 8 | [6 empty] | 22 | 2026-09-07 | [10 empty] | V 4 |  | ct3 | V 4 | VS2 | [7 empty] | M27 | P5
2026-09-08 | LD 59,60,61,62,63 | 14 | UNLD 59,60 OX | 8/9/26 @ 20:00 | 8 | [6 empty] | 22 | 2026-09-08 |  |  |  |  | >> | 59 | 60 | 61 | 62 | 63 | V 5 |  |  | V 5 | ad1 | ad2 | ad3 | rd1 | rd2 | rd3 |  | DISTRICT X
2026-09-09 | UNLD 61,62,63 OX | 14 |  | District X | 8 | [6 empty] | 22 | 2026-09-09 | [10 empty] | P2 | P8 | P14 | P20 | a1 | a2 | a3 | a4 | a5 | a6 |  | K9
2026-09-10 |  | 14 |  | 10 Pole Kayam | 8 | [6 empty] | 22 | 2026-09-10 | [10 empty] | P3 | P9 | P15 | P21 | ct1 | ct2 | ct3 | ct4 | ct5 |  |  | M24 | P2
2026-09-11 | 15 FINISH | 15 |  | KMMMMK | 8 | [6 empty] | 23 | 2026-09-11 | [10 empty] | P4 | P10 | P16 | X1 | Vb1 | Vb2 | [5 empty] | M25 | P3
2026-09-12 |  | 15 |  | Palmerstown Estate | 8 | [6 empty] | 23 | 2026-09-12 | [10 empty] | P5 | P11 | P17 | X2 | sb1 | sb2 | sb3 | sb4 |  |  |  | M26 F | P4
2026-09-13 |  |  |  | Dublin | 8 | [6 empty] | 8 | 2026-09-13 | [10 empty] | P6 | P12 | P18 | X3 | [7 empty] | M27 | P5
2026-09-14 |  |  |  | 14/9/26 @ 20:00 | 8 | [6 empty] | 8 | 2026-09-14 | [10 empty] | P7 | P13 | P19 | X4 | [7 empty] | K10 | P6
2026-09-15 |  |  |  | BREAK | 8 | [6 empty] | 8 | 2026-09-15 | [10 empty] | K1 | K8 |  | M21 | M27 | s3
2026-09-16 |  |  |  | BREAK | 8 | [6 empty] | 8 | 2026-09-16 | [10 empty] | K2 | K9 | m5 | M24 | M28 | s4 | K9 | M24 | P2 | P6 |  | ct5
2026-09-17 |  |  |  | BREAK | 8 | LD 58,59 | CM17 |  |  |  |  | 8 | 2026-09-17 | [10 empty] | K3 | K10 | m6 | M25 | SC1 | T1 | K10 | M25 | P3 | ct5 |  | sb2
2026-09-18 |  |  |  |  | 8 | [6 empty] | 8 | 2026-09-18 | [10 empty] | K6 | K11 | m7 | M26 F | SC2 | T2 |  | M26 F | P4 | sb2 | 64 | << | 64
2026-09-19 | CREW PARTY? |  |  | CREW PARTY? |  |  | CREW PARTY? |  |  | CREW PARTY? |  | 0 | 2026-09-19 | [10 empty] | K7 |  | m8 |  | SC3 | T3 |  | M27 | P5 |  | 65 | << | 65
2026-09-20 | [11 empty] | 0 | 2026-09-20
2026-09-21 |  |  |  | UNLD 58, 59 | [7 empty] | 0 | 2026-09-21
2026-09-22 | [11 empty] | 0 | 2026-09-22
2026-09-23 | [11 empty] | 0 | 2026-09-23
2026-09-24 | [11 empty] | 0 | 2026-09-24
2026-09-25 | [11 empty] | 0 | 2026-09-25
2026-09-26 | [11 empty] | 0 | 2026-09-26
2026-09-27 | [11 empty] | 0 | 2026-09-27
2026-09-28 | [11 empty] | 0 | 2026-09-28
2026-09-29 | [11 empty] | 0 | 2026-09-29
2026-09-30 | [11 empty] | 0 | 2026-09-30
2026-10-01 | [11 empty] | 0 | 2026-10-01
2026-10-02 | [11 empty] | 0 | 2026-10-02
2026-10-03 | [11 empty] | 0 | 2026-10-03
2026-10-04 | [11 empty] | 0 | 2026-10-04
2026-10-05 | [11 empty] | 0 | 2026-10-05
2026-10-06 | [12 empty] | 2026-10-06
2026-10-07 | [12 empty] | 2026-10-07
2026-10-08 | [12 empty] | 2026-10-08
2026-10-09 | [12 empty] | 2026-10-09
Note on L16: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. kelly 5. Ethan 6. Rich 7. Ross 8. Jim 9. Imogen 10. Nina
Note on B20: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat
Note on C20: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat
Note on C23: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Ethan 8. Rich 9. Ross 10. Jim 11. Imogen
Note on J23: Sadie Ward: 1. Ethan 2. Rich 3. Ross 4. Jim 5. Imogen
Note on L23: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Nina
Note on J28: Sadie Ward: 1. Johnny E 2. Jonny L 3. Amelie
Note on L28: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Johnny E 6. Jonny L 7. Nina 8. Amelie
Note on K35: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Johnny E 6. Jonny L 7. Nina 8. Amelie
Note on I40: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Johnny E 6. Jonny L 7. Nina 8. Amelie
Note on C43: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Ethan 8. Rich 9. Ross 10. Jim 11. Imogen 1. Cameron 2. Johnny E 3. Nina 4. Jonny L 5. Amelie
Note on G43: Sadie Ward: 1. Cameron 2. Johnny E 3. Nina 4. Jonny L 5. Amelie
Note on I43: Sadie Ward: 1. Jesse 2. Marley 3. Kelly
Note on C46: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Ethan 8. Rich 9. Ross 10. Jim 11. Imogen
Note on E46: Sadie Ward: 1. Cameron 2. Johnny E 3. Nina 4. Jonny L 5. Amelie
Note on I46: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Johnny E 6. Jonny L 7. Nina 8. Amelie
Note on C47: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Rich 8. Jim 9. Imogen
Note on E47: Sadie Ward: 1. Ross 2. Ethan
Note on F47: Sadie Ward: 1. Ross 2. Ethan
Note on E49: Sadie Ward: 1. Alice 2. William 3. Raunak 4. Nadine 5. Agus
Note on F49: Sadie Ward: 1. Alice 2. William 3. Raunak 4. Nadine 5. Angus 6. Ethan 7. Ross
Note on C50: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Rich 8. Jim 9. Imogen 10. Jonny 11. Amelie
Note on I50: Sadie Ward: 1. Jesse 2. Cameron 3. Marley 4. Kelly 5. Johnny E 6. Nina
Note on J50: Sadie Ward: 1. Jonny L 2. Amelie
Note on F52: Sadie Ward: 1. Alice 2. William 3. Raunak 4. Angus 5. Ethan 6. Ross 7. Jesse 8. Nina 9. Anna M - TEMP
Note on G52: Sadie Ward: 1. Anna M
Note on I52: Sadie Ward: 1. Johnny E 2. Cameron 3. Marley 4. Kelly
Note on J52: Sadie Ward: 1. Nina 2. Jesse
Note on F58: Sadie Ward: 1. Alice 2. William 3. Raunak 4. Angus 5. Ethan 6. Ross 7. Jesse 8. Nina
Note on G58: Sadie Ward: 1. Anna M
Note on F61: Sadie Ward: 1. William 2. Raunak 3. Ethan 4. Ross
Note on G61: Sadie Ward: 1. Jesse 2. Nina 3. Alice 4. Angus
Note on I61: Sadie Ward: 1. Jesse 2. Nina 3. Alice 4. Angus 5. Johnny E 6. Cameron 7. Marley 8. Kelly
Note on F71: Sadie Ward: 1. William 2. Raunak 3. Ethan 4. Ross
Note on I71: Sadie Ward: 1. Jesse 2. Nina 3. Alice 4. Angus 5. Johnny E 6. Cameron 7. Marley 8. Kelly
Note on C72: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Alex M 5. Ellie 6. Cat 7. Rich 8. Jim 9. Imogen 10. Jonny 11. Amelie
Note on F72: Sadie Ward: 1. William 2. Raunak 3. Ethan 4. Ross 5. Johnny E 6. Angus
Note on H72: Sadie Ward: GREEN (IN VN07 EOE) 1. Johnny E 2. Angus BLUE (IN EN59 GHJ) 1. Marley 2. Cameron 3. Alice 4. Nina
Note on I72: Sadie Ward: 1. Jesse 2. Kelly
Note on J72: Sadie Ward: 1. Aisha
Note on L72: Sadie Ward: 1. Cameron 2. Marley 3. Nina 4. Alice 5. Aisha
Note on C73: Sadie Ward: 1. Max 2. Martin 3. Dulcie 4. Cat 5. Imogen 6. Jonny 7. Amelie
Note on D73: Sadie Ward: > Blue 1. Rich 2. Jim 3. Ellie > Green 1. Alex M
Note on F73: Sadie Ward: 1. William 2. Raunak 3. Ethan 4. Ross 5. Alex M 6. Johnny E 7. Angus 8. Anna M - TEMP 9. Ben - TEMP 10. Mupps - TEMP
Note on G73: Sadie Ward: 1. Anna M 2. Temp TBC 3. Martin F
Note on L73: Sadie Ward: 1. Cameron 2. Marley 3. Nina 4. Alice 5. Aisha 6. Rich 7. Jim 8. Ellie
Note on C74: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny 5. Amelie
Note on D74: Sadie Ward: CM11 1. Dulcie 2. Cat CM18 1. Martin 2. Imogen
Note on I74: Sadie Ward: 1. Jesse 2. Kelly 3. Cat 4. Dulcie
Note on D75: Sadie Ward: Hotel in Bremen Max Amelie Jonny
Note on D76: Sadie Ward: Hook > Harwich Max Jonny Amelie
Note on G77: Sadie Ward: 1. Anna M 2. Mupps
Note on C78: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny 5. Amelie 6. Jim 7. Ellie 8. Rich 9. Alex M
Note on F78: Sadie Ward: 1. Ben 2. Raunak 3. Ethan 4. Ross 5. Ben 6. Johnny E 7. Angus
Note on G78: Sadie Ward: 1. Alex M - ETHAN DRIVE DUCK
Note on I78: Sadie Ward: 1. Jesse 2. Kelly 3. Cat 4. Dulcie
Note on J78: Sadie Ward: 1. Rich 2. Jim 3. Ellie
Note on L78: Sadie Ward: 1. Marley 2. Nina 3. Alice 4. Aisha 5. Cameron
Note on C79: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny 5. Amelie 6. Jim 7. Ellie 8. Rich 9. Alex M 10. Dulcie 11. Cat
Note on G79: Sadie Ward: 1. Dulcie 2. Kat ETHAN DRIVE DUCK
Note on I79: Sadie Ward: 1. Jesse 2. Kelly
Note on I82: Sadie Ward: 1. Jesse 2. Kelly
Note on F83: Sadie Ward: 1. Ben 2. Raunak 3. Ethan 4. Ross 5. Ben 6. Johnny E 7. Angus
Note on I83: Sadie Ward: 1. Jesse 2. Kelly
Note on G84: Sadie Ward: Ben finish
Note on H85: Sadie Ward: 1. Kasper 2. Niko 3. Alex
Note on I85: Sadie Ward: 1. Jesse 2. Kelly 3. Cameron 4. Niko - TEMP 5. Alex (scottish) - TEMP 6. Kasper - TEMP
Note on J85: Sadie Ward: 1. Cameron
Note on L85: Sadie Ward: 1. Marley 2. Nina 3. Alice 4. Aisha
Note on F86: Sadie Ward: 1. Ben 2. Raunak 3. Ross 4. Angus
Note on G86: Sadie Ward: 1. Ethan DRIVE DUCK 2. Johnny E
Note on L86: Sadie Ward: 1. Marley 2. Nina 3. Alice 4. Aisha 5. Johnny E 6. Ethan
Note on I90: Sadie Ward: 1. Jesse 2. Kelly 3. Cameron
Note on J90: Sadie Ward: 1. Kasper 2. Niko 3. Alex
Note on F91: Sadie Ward: 1. Ben 2. Raunak 3. Ross 4. Angus 5. Nina 6. Ethan 7. Johnny E
Note on I91: Sadie Ward: 1. Jesse 2. Kelly 3. Cam 4. Aisha
Note on J91: Sadie Ward: Aisha
Note on K91: Sadie Ward: 1. Nina 2. Ethan (driving duck) 3. Johnny E
Note on L91: Sadie Ward: 1. Marley 2. Alice 3. Aisha
Note on L92: Sadie Ward: 1. Marley 2. Alice
Note on F93: Sadie Ward: 1. Ben 2. Raunak 3. Ross 4. Angus 5. Nina 6. Ethan 7. Johnny E 8. Alice 9. Marley
Note on K93: Sadie Ward: 1. Alice 2. Marley
Note on F96: Sadie Ward: 1. Ben 2. Raunak 3. Ross 4. Angus 5. Nina 6. Ethan 7. Johnny E 8. Alice 9. Marley
Note on E98: Sadie Ward: 1. Marley 2. Angus 3. Raunak 4. Alice
Note on F98: Sadie Ward: 1. Ross 2. Nina 3. Ethan 4. Johnny E 5. Ben
Note on I98: Sadie Ward: 1. Marley 2. Angus 3. Raunak 4. Cameron 5. Jesse 6. Kelly 7. Alice 8. Aisha
Note on E100: Sadie Ward: NINA BEN
Note on F100: Sadie Ward: 1. Ross 3. Ethan 4. johnny E
Note on C103: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny 5. Amelie 6. Jim 7. Ellie 8. Rich 9. Alex M 10. Dulcie 11. Cat
Note on C104: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny L 5. Amelie 6. Jim 7. Ellie 8. Rich 9. Alex M 10. Dulcie 11. Cat 12. Johnny E 13. Ross 14. Ethan
Note on E104: Sadie Ward: 1. Ross 2. Ethan 3. Johnny E
Note on H111: Sadie Ward: Aisha
Note on C112: Sadie Ward: 1. Max 2. Martin 3. Imogen 4. Jonny L 5. Amelie 6. Jim 7. Ellie 8. Rich 9. Alex M 10. Dulcie 11. Cat 12. Kelly 13. Johnny E 14. Ethan 15. Cameron
Note on D112: Sadie Ward: 1. Ross 2. TBC 3. Angus
Note on F112: Sadie Ward: 1. Ross 2. Marley 3. Jesse 4. William 5. Raunak 6. Nadine 7. Alice 8. Angus
Note on H112: Sadie Ward: Green 1. Jesse 2. Angus 3. Raunak 4. Marley 5. Alice RED 1. Kelly 2. Cameron
Note on E128: Sadie Ward: NINA
Note on F128: Sadie Ward: 1. Ross 2. Marley 3. Jesse 4. William 5. Raunak 6. Nadine 7. Nina 8. Angus